## Completed
Project | Change Order/Service Order/Service Change Order | Status
Maestro Firewall Upgrade | CR-CAP-038 Maestro GEN_SEC Refresh | Aug 27/25 - Signed Aug 26/25 - approved for signing; Province to confirm signatory Aug 7/25 - V3 sent to Province Aug 6/25 - V2.3 rec'd July 8/25 - V1.1 sent to Province July 7/25 - V1.1 with Cathy/Joyce July 4/25 - Joyce updating table June 27/25 - internal meeting scheduled for July 4 June 24/25 - with Sam / Joyce June 12/25 - Still waiting on quotes for a few replacement items May 27/25 - Pending client design approval and final quotes from vendors. May 15/25 - Brian and Sam discussing Apr 22/25 - No Tech Stew approval needed, Province has V1 Apr 1/25 - V1 sent to Province, pending tech stew Mar 31/25 - with Sam
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-053 CITZ MCS OpenShift Server | Aug 14/25 - Signed July 30/25 - V3 sent to Province July 28/25 - V2.1 rec'd July 22/25 - V1.1 sent to Province July 4/25 - V1 sent to Province June 25/25 - with Cathy / Adam
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-056 MCS OpenShift Gold Cl Ext Mtc | Aug 21/25 - Signed Aug 18/25 - moved to final; waiting for PR July 29/25 - response sent to Province July 28/25 - Province question with Sam July 23/25 - V3 sent to Province July 21/25 - V2 rec'd July 8/25 - V1 sent to Province July 7/25 - with Cathy
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-067 MCS OpenShift Gold Cluster | Oct 29/25 - Signed Oct 23/25 - quote rec'd; V3 sent to Province Oct 14/25 - waiting for timeline of new switches; getting new quote Oct 8/25 - question to Tyler Sept 25/25 - follow up with Chris Sept 17/25 - with Chris to confirm refresh dates Sept 10/25 - V2 rec'd; Province requested less than 1 year; with Procurement Aug 20/25 - V1 sent to Province Aug 19/25 - with Cathy
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-068 MCS OpenShift Custom HW | Sept 11/25 - Signed Aug 26/25 - V1 sent to Province Aug 25/25 - with Sian
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-069 Redhat OpenShift MCS Servers | Sept 19/25 - Signed Sept 17/25 - V5 sent to Province Sept 16/25 - V4 rec'd Sept 10/25 - V3 sent to Province Sept 9/25 - V2 rec'd; with Joyce Aug 28/25 - V1 sent to Province
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-073 MCS OpenShift Custom HW | Oct 24/25 - Signed Oct 23/25 - V2 rec'd; V3 and V3.1 sent to Province; Adobe Sign Oct 20/25 - V1.1 sent to Province Oct 15/25 - Sam to confirm if new quotes correct Sept 23/25 - Province asked some clarifying questions around the ordering of this proposed hardware Sept 9/25 - on hold; Sam reviewing port counts which may change Sept 3/25 - V1 sent to Province Aug 28/25 - with Cathy / Bruce
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-074 Redhat OpenShift MCS Srvrs | Oct 1/25 - Signed Sept 26/25 - Adobe Sign Sept 18/25 - V1 sent to Province Sept 17/25 - with Tyler
Public Cloud MCS OpenShift Project (ROSA) | CR-CAP-078 Redhat OpenShift MCS Srvrs | Oct 27/25 - Signed Oct 23/25 - quote rec'd; with Chris for PR Oct 22/25 - approved for signing; quote requested Oct 15/25 - V3 sent to Province (upgrade removed) Oct 14/25 - V2 rec'd Oct 1/25 - V1 sent to Province Sept 29/25 - with Tyler
MCCS - Service Expansion | CR-CAP-083 MCCS Virtual Connections | Nov 21/25 - Adobe Sign Nov 4/25 - Sam confirmed which VC get standup fee Oct 27/25 - V1.1 sent to Province Oct 24/25 - V1.1 with Shane/Cathy Oct 22/25 - V1.1 with Killian / Cathy Oct 8/25 - V1 sent to Province Oct 2/25 - with Cathy/Killian
MCCS - Service Expansion | CR-CAP-087 MCCS Azure VCs | Dec 2/25 - re-sent to Adobe Sign Nov 27/25 - Adobe Sign Nov 18/25 - V1 sent to Province Nov 14/25 - with Yale / Cathy
MCCS - Service Expansion | CR-CAP-101 MCCS CAS VCs | Jan 22/26 - Adobe Sign Dec 19/25 - V1 sent to Province
MCCS - Service Expansion | CR-CAP-128 Amd CAP-101 MCCS CAS VCs | Mar 30/26 - Adobe Sign Mar 24/26 - Province question with Shane; V3 sent to Province Mar 19/26 - V2 rec'd; with RM (Kevin) Mar 17/26 - V1 sent to Province Mar 12/26 - with Tyler
RTMC Remediation Project | SCO-PROV-355 RTMC Professional Services Remediation | Jan 4/22 - Signed Dec 17/21 - V3 submitted to Province Dec 15/21 - with Sian for approval Dec 14/21 - with Cathy to review Province comments. Nov 22/21 - submitted to Province Nov 18/21 - with Serge for approval Nov 9/21 - Province has questions re effort and SW Oct 26/21 - pricing submitted to Province Oct 12/21 - internal meeting to discuss Province feedback Sept 28/21 - first model sent to Province; internally AS thinks Q4
Public Cloud MCS OpenShift Project (ROSA) | SCO-PROV-383 Public Cloud MCS OpenShift | Mar 25/22 - Signed Mar 24/22 - with Province for signing Mar 22/22 - with Serge for signing Mar 7/22 - submitted to Province Mar 3/22 - with Serge for approval Mar 2/22 - with Jen for review/updating Feb 10/22 - submitted to Province Feb 3/22 - with Sian for approval Feb 2/22 - with Cathy/Jen for review Jan 10/22 - SCO drafted; Jen to provide SOW
MS Defender Proof of Concept | SCO-PROV-416 Antivirus Product Evaluation | June 29/22 - Signed June 23/22 - V4 sent to Province June 20/22 - V3 received June 2/22 - V2 submitted to Province June 1/22 - V2 with Rian and Cathy for review Apr 20/22 - submitted to Province Apr 13/22 - with Serge for approval Apr 12/22 - Rian reviewing with Lori Collins Apr 6/22 - with Rian for review
RTMC Remediation Project | SCO-PROV-453 Amd SCO-355 RTMC PS Remed | Oct 14/22 - Signed Oct 13/22 - V2 rec'd Oct 4/22 - V1 sent to Province
Next Gen Shared File Phase 5 | SCO-PROV-463 Next Gen Shared File Phase 5 | June 30/23 - Signed June 27/23 - V5 sent to Province June 27/23 - V4 back from Province - would like sign off prior to June 30 June 20/23 - V3 sent to Province June 19/23 - SCO out for review internally June 19/23 - SOW approved, SCO in draft June 6/23 - During BN/BA meeting Brian asked to have the SCO ready to go so that once the BA is approved we can proceed right away Apr 27/23 - SOW sent to Province Mar 27/23 - Province approved to move forward to SOW/SCO, awaiting internal SOW creation Dec 2/22 - Lori C. advised this will be reverting back to BA Nov 24/22 - V2 submitted to Province Nov 23/22 - V2 with Sian for approval Nov 22/22 - submitted to Province
OpenVMS Hardware Upgrade | SCO-PROV-466 OpenVMS Custom Servers | Dec 5/22 - Signed Dec 3/22 - Moved to FINAL and sent to Sian/Serge for approval Dec 3/22 - V4 recevied back from the Province Dec 3/22 - V3 sent to Province Dec 2/22 - Edits made, back with Lori/Cathy Dec 1/22 - V2 back from Province, with Cathy/Lori C. for review Nov 28/22 - SCO submitted to Province Nov 28/22 with Sian for approval to submit to Province Nov 25/22 - Followed up with vendor re: hardware availability, vendor confirmed Nov 23/22 - hold on sending OpenVMS refresh to the Province, waiting to hear from vendor Nov 22/22 - with Jen and Cathy for review
RTMC Remediation Project | SCO-PROV-479 Amend SCO-453 RTMC PS Remed | Feb 9/23 - Signed Feb 8/23 - With Province for signature Feb 8/23 - With Sian for signature approval Feb 7/23 - V4 sent to Province Feb 3/23 - Province question with Sharon Jan 31/23 - V3 sent to Province Jan 31/23 - Followed up with Sharon Jan 25/23 - Sent Sharon T to answer question Jan 20/23 - Sent to Sian Jan 20/23 - Province sent V2 back with a Q Jan 10/23 - V1 Sent to Province Jan 9/23 - With Sian
Patch Management Phase 2 | SCO-PROV-482 Patch Management Phase 2 | Feb 16/23 - Completed Feb 16/23 - Final sent to Province for signature Feb 15/23 - With Sian for signature approval Feb 13/23 - Province requested to move to Final Feb 8/23 - V3 Sent to Province Feb 8/23 - With Cathy/Lori Feb 3/23 - V2 back from Province with comments Jan 27/23 - Sent to Province Jan 27/23 - With Sian Jan 26/23 - With Lori/Cathy for review Jan 26/23 - Requested pricing table from Cathy Jan 25/23 - With Jen to draft
IT Modernization Roadmap | SCO-PROV-484 IT Modernization Roadmap | Mar 14/23 - Completed/signed Mar 10/23 - Final sent to Province Mar 10/23 - Province requested to move to signature, with Sian Mar 7/23 - V4 sent to Province Mar 2/23 - Q with Cathy Feb 22/23 - With Jen to amend/review Feb 22/23 - Sent to Cathy for review Feb 16/23 - V3 back from Province Feb 10/23 - V2 sent to Province Feb 9/23 - Updates to SOW, V2 with Lori for review Feb 1/23 - V1 sent to Province Feb 1/23 - With Sian Feb 1/23 - Draft sent to Cathy/Lori for review Jan 31/23 - Lori Sent SOW
SDN Release 4 | SCO-PROV-515 SDN Release 4 Implementation | Aug 23/23 - Signed Aug 21/23 - Province agreed to move to Final, with Sian Aug 15/23 - V5 sent to Province Aug 14/23 - V4 back from Province Aug 9/23 - Rian talking to Emma Aug 8/23 - Province responded with statement regarding SOWs not being ROM picing, internal convo needed, emailed Michelle Aug 1/23 - V3 sent to Province July 27/23 - V2 back from Province, question with Chris July 14/23 - V1 sent to Province July 14/23 - With Lori C. and Sian for approval July 12/23 - Decision to remove licenses from this SCO and scribe them at a later date, with internal team for review July 12/23 - SOW rec'd from vendor, internal review scheduled for today July 10/23 - Cathy followed up with Vendor July 6/23 - Cathy getting quotes from vendors June 23/23 - Michelle C following up with Vendor quotes June 19/23 - Cathy emailed Chris to obtain vendor quotes for the external resources June 19/23 - Followed up and scheduled an internal mtg June 15/23 - Draft started, emailed Chris/Cathy for the updated table June 13/23 - SOW Rel 4 approved May 5/23 - SOW with Province who have asked for an early project start, so SCO number assigned so a WBS code can be created
MFA for BC SAG | SCO-PROV-516 Amd SCO-443 MFA for BC SAG | Nov 28/23 - Completed Nov 27/23 - Final sent to Province Nov 27/23 - Province agreed to move to final, with Sian Nov 6/23 - V12 sent to Province Oct 27/23 - V11 rec'd; with Cathy/Chris Oct 25/23 - V10 sent to Province Oct 24/23 - V9 rec'd from Province Oct 19/23 - V8.1 submitted to Province Oct 16/23 - with Cathy Oct 8/23 - V8.1 with Cathy/Jen Oct 5/23 - Followed up with Chris Sept 19/23 - followed up with Chris re: his take-aways from meeting Sept 11/23 - internal meeting scheduled for Sept 14 Sept 5/23 - V8 send to Province Aug 22/23 - Question out to Ops again, then back to Cathy Aug 9/23- V7 back from Province, question with Cathy Aug 1/23 - V6 sent to Province July 17/23 - Emailed group for clarity July 11/23 - Followed up with Chris again July 6/23 - Follwed up with Chris/Lori June 27/23 - Internal question out to Lori and Chris June 23/23 - V5 back from Province June 16/23 - V4 sent to Province June 15/23 - New pricing from Cathy June 13/23 - Internal meeting scheduled for June 15 June 12/23 - V4 with Lori/Cathy to answer comments June 8/23 - V3 back from Province June 5/23 - V2 sent to Province June 5/23 - With Cathy to format pricing May 18/23 - V1 sent to Province May 18/23 - With Sian for approval May 16/23 - Followed up with Lori May 10/23 - Sent V1 to Lori for approval May 3/23 - Followed up with Lori Apr 26/23 - Sent to Lori for approval Mar 28/23 - With Cathy Mar 27/23 - With Cathy/Lori for review Mar 22/23 - Pricing provided
Shared File for BCPS Phase 2 | SCO-PROV-526 BCPS Shared File Solution Ph 1 | June 30/23 - completed June 20/23 - V1 sent to Province for review June 19/23 - V1 sent to Sian for approval June 19/23 - Draft SCO with Rian for review June 16/23 - Get started on SCO, pending answer from Province
Mainframe Processor Upgrade | SCO-PROV-536 MF Processor Refresh | Nov 16/23 - Signed Nov 11/23 - V4.1 rec'd Oct 30/23 - V3 sent to Province Oct 11/23 - V2 rec'd from Province Oct 5/23 - V1.1 sent to Province Oct 4/23 - V1 submitted to Province Oct 3/23 - With Lori C. Sept 29/23 - with Tyler for approval Sept 27/23 - Cathy getting updated quotes Sept 26/23 - updates sent to Cathy for review Sept 25/23 - V1 with Cathy / Rian for review Sept 13/23 - SOW approved Aug 12/23 - SOW expected back from Province shortly Aug 2/23 - SCO number requested, asked for latest version of SOW which is still v1.3 June 19/23 - Rian working on SOW
NRS VDI Service PoC | SCO-PROV-558 NRS VDI Service POC | Oct 24/23 - Signed Oct 19/23 - with Province for signing Oct 17/23 - SOW approved Oct 16/23 - V5 sent to Province Oct 13/23 - V4 rec'd from Province Oct 12/23 - V3 sent to Province Oct 10/23 - V1 sent to Province, if/when V2 comes back from Province need to talk to Chris S./Rian, suggested business completion date from Rian is 2 months after requirements sign-off, not Dec 31 Oct 10/23 - With Lori C., Province requested a name change to reflect the NRS as this is for the whole sector, not an individual Ministry Oct 6/23 - With Tyler for approval Sept 29/23 - V1 with Rian for review Sept 27/23 - V1 with Cathy / Rian for review Sept 26/23 - Province requested SOW and SCO together
Patch Management Phase 3A | SCO-PROV-562 Patch Mgmt Ph 3A | Nov 2/23 - Signed Oct 25/23 - V3 sent to Province Oct 20/23 - V2.1 back from Province Oct 13/23 - V1 sent to Province Oct 12/23 - With Tyler Oct 12/23 - With Rian/Cathy for review Oct 12/23 - Drafing SCO
Shared File for BCPS Phase 2 | SCO-PROV-565 BCPS Custom Hardware | Nov 8/23 - Completed Nov 8/23 - Final version sent to Province Nov 7/23 - Province accepted V3, final with Sian for approval Nov 6/23 - V3 sent to Province Nov 3/23 - requested Province expedite review; Province question with Bruce/Rian Oct 30/23 - V1 sent to Province Oct 30/23 - With Sian Oct 27/23 - with Tyler Oct 26/23 - with Rian / Cathy
NRS VDI Service PoC | SCO-PROV-576 Amd SCO-558 NRS VDI Service POC | Dec 14/23 - Signed Dec 12/23 - V2 rec'd Nov 28/23 - V1 sent to Province
SDN Release 4 | SCO-PROV-577 Amd SCO-515 SDN Rel4 Impl | Nov 27/23 - Signed Nov 24/23 - Final with Sian Nov 24/23 - V2 back from Province Nov 9/23 - V1 sent to Province Nov 8/23 - with Sian Nov 7/23 - with Michelle C.
Zscaler Initiative 1 and 2 | SCO-PROV-578 Zscaler Design: Initiative 1 | Dec 1/23 - Signed Dec 1/23 - Final version sent to Province Dec 1/23 - Confirmed with Joshua re: Province proposed project end date, with Sian for signature Dec 1/23 - V2.1 back from Province ok to move to final if we accept proposed end date Nov 30/23 - V1 sent to Province Nov 30/23 - SOW still being reviewed, request to send updated SCO over to Province from Sian/Rian Waiting for SOW approval (there will need to be a 2nd SCO for Initiave 2) Oct 27/23 - with Rian / Cathy
Zscaler Initiative 1 and 2 | SCO-PROV-592 Zscaler Design - Init 2 | Jan 26/24 - Signed Jan 26/24 - V2 rec'd Jan 23/24 - V1 sent to Province
Patch Management Phase 3A | SCO-PROV-602 Amd SCO-562 Patch Mgt Ph 3A | Feb 23/24 - Signed Feb 12/24 - V1 sent to Province
Zscaler Initiative 1 and 2 | SCO-PROV-609 Amd SCO-578 Zscaler Design-Init 1 | Mar 8/24 - Signed Feb 22/24 - V1 sent to Province Feb 21/24 - with Erwin
Zscaler Initiative 1 and 2 | SCO-PROV-610 Amd SCO-592 Zscaler Design-Init 2 | Mar 8/24 - Signed Feb 22/24 - V1 sent to Province Feb 21/24 - with Erwin
Microsoft Defender for Endpoint (MDE) Expansion | SCO-PROV-639 MS Defender Ph1 | May 28/24 - Signed May 22/24 - V3 sent to Province May 21/24 - V2.1 rec'd May 15/24 - V1 sent to Province
Zscaler Initiative 3 | SCO-PROV-656 Network Function Virtualization (NFV) Formerly: Zscaler Common Infrastructure Standup: Initiative 3 | Aug 7/24 - Signed July 29/24 - V3 sent to Province July 26/24 - V2 rec'd July 18/24 - V1.1 sent to Province July 11/24 - V1 sent to Province July 11/24 - With Sian July 11/24 - With Tyler July 10/24 - SOW approved, SCO with Cathy/Nicole for review June 14/24 - waiting for approved SOW June 10/24 - with Rian/Jen
Zscaler Initiative 3 | SCO-PROV-657 BCPS Zscaler Implementation Support: Initiative 3 | Aug 7/24 - Signed July 29/24 - V3 sent to Province July 26/24 - V2 rec'd; with Tyler July 18/24 - sent to Province
Patch Management Phase 3B | SCO-PROV-662 Patch Mgmt Phase 3B | Sept 20/24 - Signed Sept 12/24 - V4 rec'd; V5 sent to Province Aug 29/24 - V3.1 sent to Province Aug 28/24 - question from Province with Cathy Aug 26/24 - V2.2 rec'd; V3 sent to Province Aug 13/24 - V1 sent to Province Aug 7/24 - with Tyler Aug 2/24 - with Nicole/Cathy
Microsoft Azure Arc | SCO-PROV-673 MS Azure Arc | Oct 4/24 - Signed Sept 23/24 - V1 sent to Province Sept 19/24 - with Sian for approval Sept 11/24 - SOW with Province; SCO drafted
SDN Release 5 | SCO-PROV-676 SDN Release 5 | Nov 7/24 - Signed Oct 28/24 - V2.1 sent to Province Oct 25/24 - V2.1 with Michelle Oct 24/24 - V2 sent to Province Oct 23/24 - Comment back from Province Sept 24/24 - V1 sent to Province Sept 24/24 - With Tyler, with Sian Sept 24/24 - Feedback rec'd from Rian/Cathy Sept 20/24 - SOW approved July 18/24 - Options Doc sent to client - waiting for approval
Tenable Pilot (Addition) | SCO-PROV-677 Tenable | Oct 8/24 - Signed Sept 24/24 - V1 sent to Province Sept 24/24 - With Tyler, with Sian Sept 24/24 - With Cathy/Rian Sept 20/24 - SOW approved
CCCS Sensors PAW Implementation Phase 1 | SCO-PROV-684 Security Enhancement Program | Oct 30/24 - Signed Oct 29/24 - Final sent to Province Oct 28/24 - Move to final, with Sian Oct 28/24 - V3 sent back to Province Oct 28/24 V2 back from Province Oct 23/24 - V1 sent to Province Oct 22/24 - With Tyler, with Sian Oct 22/24 - With Rian/Joyce for review Oct 21/24 - SOW approved Oct 18/24 - SCO drafted, awaiting SOW approval
Zscaler Initiative 3 | SCO-PROV-690 Amd SCO-656 NW Funct Virtualization | Dec 4/24 - Signed Nov 6/24 - V1 sent to Province Nov 5/24 - with Sian Oct 8/24 - Erwin submitting PCR
MCCS - Service Expansion | SCO-PROV-696 Amd SCO-579 MCCS | Dec 17/24 - Province sent Final Dec 12/24 - Final sent to Province Dec 11/24 - Province agreed to move to final, with Elaine Dec 2/24 - V1 sent to Province Dec 2/24 - With Tyler, with Sian Nov 20/24 - Killian requested to extend end date, waiting on approved PCR
Tenable Pilot (Addition) | SCO-PROV-702 Amd SCO-677 Tenable | Jan 29/25 - Signed Dec 16/24 - V1 sent to Province
CCCS Sensors | SCO-PROV-704 Amd684 SEP(CCCS Sens-Ph2) | Feb 26/25 - Signed Jan 20/25 - V1 sent to Province Jan 17/25 - with Sian
PAW Implementation Phase 2a | SCO-PROV-705 SEP PAW Impl Ph2A | Feb 24/25 - Signed Feb 13/25 - V4 rec'd; V5 sent to Province Feb 7/25 - V3 sent to Province Feb 6/25 - V2 rec'd; with Nicole / Erwin Jan 28/25 - V1 sent to Province Jan 27/25 - with Tyler
Enhanced Logging | SCO-PROV-706 SEP Enhanced Logging | Feb 27/25 - Signed Feb 18/25 - V3 sent to Province Feb 13/25 - V2 rec'd Jan 30/25 - V1 sent to Province Jan 29/25 - Emma to approved revised SOW; SCO with Tyler
SDN Release 5 | SCO-PROV-708 Amd SCO-676 SDN Rel 5 | Feb 7/25 - Adobe Sign Feb 3/25 - V1 sent to Province
Maestro Firewall Upgrade | SCO-PROV-709 PS ChkPt Maestro FW Imp | Feb 25/25 - Signed Feb 25/25 - V3 re-sent Feb 13/25 - V3 sent to Province Feb 13/25 - V2 rec'd; with Joyce/Sam Feb 7/25 - V1.1 sent to Province Feb 3/25 - with Rian / Cathy
3PG Refresh | SCO-PROV-712 3PG Refresh (Professional Services) | Mar 5/25 - Signed Feb 26/25 - V1.1 sent to Province Feb 25/25 - V1 sent to Province Feb 11/25 - approved to submit; holding until CAP for 3PG Refresh submitted Jan 30/25 - with Sam Jan 27/25 - with Rian, Sam and Cathy
Maestro Firewall Upgrade | SCO-PROV-720 Maestro Firewall Implementation | Mar 27/25 - Signed Mar 14/25 - V1 sent to Province
Defender for Servers | SCO-PROV-728 Defender Anti-Virus | Apr 28/25 - Signed Apr 28/25 - Move to final, sent via AdobeSign Apr 25/25 - V2 back from Province Apr 17/25 - V1 sent to Province Apr 17/25 - With Tyler, with Sian Apr 17/25 - With Nicole/Cathy for review Apr 14/25 - SOW approved
AV Defender for Linux | SCO-PROV-728 Defender Anti-Virus | Apr 28/25 - Completed Apr 28/25 - Move to final, sent via AdobeSign Apr 25/25 - V2 back from Province Apr 17/25 - V1 sent to Province Apr 17/25 - With Tyler, with Sian Apr 17/25 - With Nicole/Cathy for review Apr 14/25 - SOW approved
PAW Implementation Phase 2B | SCO-PROV-729 PAW Phase 2b | Apr 24/25 - Completed Apr 24/25 - Province sent back V2, moved to Final, sent via AdobeSign Apr 17/25 - V1 sent to Province Apr 17/25 - With Tyler, with Sian Apr 17/25 - With Nicole/Cathy for review Apr 14/25 - SOW approved
Enhanced Logging Phase 2 | SCO-PROV-730 Enhanced Logging Phase 2 | June 10/25 - Adobe Sign May 27/25 - V1 sent to Province May 22/25 - with Tyler May 21/25 - with Nicole / Cathy Placeholder - need # for SOW approval
Patch Management Phase 3B | SCO-PROV-733 Amd SCO-662 Patch Mgmt Proj Date | Apr 30/25 - Signed Apr 30/25 - In AdobeSign for signautres Apr 29/25 - Approval to move to final Apr 14/25 - V1 sent to Province Apr 11/25 - With Sian Apr 10/25 - With Tyler Apr 10/25 - With Killian Apr 8/25 - Approved PCR to extend date, drafting SCO
MCCS - Service Expansion | SCO-PROV-735 MCCS Service Expansion | May 29/25 - Completed May 26/25 - Send via AS for sigs May 23/25 - Province agreed to move to final May 8/25 - V2.1 rec'd; V3 sent to Province May 6/25 - Followed up with Sian, V1 sent to Province Apr 29/25 - With Tyler, with Sian Apr 28/25 - With Killian and Cathy Apr 11/25 - SOW approved to move to SCO
Multi Cloud Connectivity | SCO-PROV-739 Multi-Cloud Connectivity Service | July 31/25 - Adobe Sign July 18/25 - V5 sent to Province July 9/25 - V4 rec'd; with Killian / Sam June 13/25 - V3 sent to Province June 6/25 - Province asked for this to be expedited May 28/25 - with Sam May 23/25 - Killians sent responses May 22/25 - with Killian / Sam May 21/25 - V2.1 rec'd May 12/25 - V1 sent to Province May 9/25 - with Joyce May 6/25 - with Rian Apr 30/25 - Back from Killian with comments - to review Apr 28/25 - With Killian Apr 11/25 - Lori M drafted SCO from approved Service Design, Jen to continue
iStore to MySC | SCO-PROV-743 iStore Replacement | July 15/25 - Signed July 10/25 - Sent via Adobe Sign July 9/25 - Province agreed to move to final July 7/25 - V5 sent to Province June 27/25 - V4 rec'd; with Rian June 4/25 - V3 sent to Province May 29/25 - V2.1 rec'd; with Rian May 22/25 - V1 sent to Province May 21/25 - with Sian
Zscaler Initiative 3 | SCO-PROV-745 Amd SCO-657 zScaler Imp Supp | June 10/25 - Signed May 28/25 - With Tyler, with Sian, V1 sent to Province May 27/25 - With Lori M. for review May 26/25 - Erwin asked for an amendment to Proj end date
CMDB Optimization (Discovery) | SCO-PROV-747 CMDB Optimization | Oct 3/25 - Signed Sept 24/25 - Michelle C confirmed 4 servers needed instead of 5; Province still reviewing Sept 19/25 - Erwin, Rian and Michelle reviewed/OK'd updated SCO: V3 and 3.1 sent to Province Sept 16/25 - updated SCO; with Rian/Michelle Aug 18/25 - V2.1 rec'd; with Rian and Michelle C July 15/25 - V1 sent to Province July 14/25 - with Rian / Cathy Reserved for early start
MFA for VDI | SCO-PROV-748 MFA for VDI | Oct 2/25 - Adobe Sign Sept 25/25 - V3 sent to Province Sept 24/25 - V2 rec'd; with Nicole / Erwin Aug 21/25 - SOW approved; V1.1 sent to Province July 22/25 - waiting for Emma's approval of revised SOW June 24/25 - V1 sent to Province June 19/25 - with Sian June 17/25 - with Tyler June 16/25 - with Erwin, Cathy, Joyce
MFA for BC SAG | SCO-PROV-752 Amd SCO-443 MFA for BC SAG | Sept 22/25 - Cancelled Sept 16/25 - Carol confirmed it can be cancelled. July 28/25 - V2.1 rec'd; with Cathy July 7/25 - V1 sent to Province July 4/25 - Dan Deane confirmed servers; SCO updated, with Tyler With Alex Thompson to confirm servers
iStore to MySC | SCO-PROV-756 Amd SCO-743 iStore Replacement | Oct 31/25 - Signed Aug 6/25 - V1.1 sent to Province Aug 1/25 - V1 sent to Province July 18/25 - with Michelle / Cathy
3PG Refresh | SCO-PROV-757 Amd SCO-712 3PG Refresh | Aug 20/25 - Signed Aug 6/25 - V1 sent to Province Aug 5/25 - with Cathy
3PG Refresh | SCO-PROV-757 Amd SCO-712 3PG Refresh | Aug 18/25 - Adobe Sign Aug 6/25 - V1 sent to Province Aug 5/25 - with Cathy
MCCS - Service Expansion | SCO-PROV-760 Amd SCO-739 MCCS | Sept 10/25 - Adobe Sign Sept 3/25 - V1 sent to Province
OpenShift GPU Enablement | SCO-PROV-765 GPU Enablement on Openshift Pilot | Dec 10/25 - Adobe Sign Dec 9/25 - V2 rec'd; V3 sent to Province Nov 24/25 - V1 sent to Province Nov 13/25 - with Rian / Cathy Nov 4/25 - early start approved by Emma Nov 3/25 - hold for further changes to SOW
3PG Refresh | SCO-PROV-768 Amd SCO-712 3PG Refresh | Dec 11/25 - Signed Nov 25/25 - V1 sent to Province Nov 24/25 - with Erwin / Cathy
3PG Refresh | SCO-PROV-768 Amd SCO-712 3PG Refresh | Dec 9/25 - Adobe Sign Nov 25/25 - V1 sent to Province Nov 24/25 - with Erwin / Cathy
iStore to MySC | SCO-PROV-771 Amd SCO-743 iStore Replacement | Jan 16/26 - Signed Jan 13/26 - V2 rec'd; Adobe Sign Dec 18/25 - V1 sent to Province Dec 17/25 - with Sian
Maestro Firewall Upgrade | SCO-PROV-772 Amd SCO-720 Maestro FW Impl | Feb 9/26 - Signed Feb 3/26 - Adobe Sign Jan 15/26 - V1 sent to Province Jan 14/26 - with Sian
MCCS - Service Expansion | SCO-PROV-773 Amd SCO-735 MCCS Srvc Exp | Feb 2/26 - Adobe Sign Jan 20/26 - V1 sent to Province Waiting for breakdown of additional hours by role
3PG Refresh | SCO-PROV-775 Amend 712 3PG Refresh | Feb 3/26 - Signed Feb 2/26 - Adobe Sign Jan 30/26 - V2 sent to ESIT-AS Jan 21/26 - V1 sent to the Province Jan 21/26 - with Sian Jan 16/26 - with Dor / Cathy
3PG Refresh | SCO-PROV-775 Amend 712 3PG Refresh | Feb 3/26 - Completed Feb 2/26 - Adobe Sign Jan 30/26 - V2 sent to ESIT-AS Jan 21/26 - V1 sent to the Province Jan 21/26 - with Sian Jan 16/26 - with Dor / Cathy
Next Gen Shared File Phase 6 | SCO-PROV-777 Amd SCO-PROV-710 PS for Next Gen SF Phase 6 | Feb 4/26 - Signed Feb 4/26 - Adobe Sign Feb 4/26 - V2 sent to ESIT- AS Jan 28/26 - V1 sent to Province Jan 26/26 - with Tyler Jan 22/26 - with Yale Ashraff
iStore to MySC | SCO-PROV-782 Amd SCO-743 iStore Repl | Mar 16/26 - Signed Feb 13/26 - V1 sent to Province
Maestro Firewall Upgrade | SCO-PROV-788 Amd SCO-709 PS ChkPt Maestro FW Imp | Mar 20/26 - Signed Mar 19/26 - Adobe Sign Mar 18/26 - V2 rec'd; V3 sent to Province Mar 3/26 - V1 sent to Province Mar 2/26 - with Michelle C/ Cathy